Project Planning Phase

Project Planning Template (Product Backlog, Sprint Planning, Stories, Story Points)

| Date | 15 February 2026 |
| --- | --- |
| Team ID |  |
| Project Name | Customer Registry |
| Maximum Marks | 5 Marks |

Product Backlog, Sprint Schedule, and Estimation (4 Marks)

Use the below template to create product backlog and sprint schedule

| Sprint | Functional Requirement (Epic) | User Story Number | User Story / Task | Story Points | Priority | Team Members |
| --- | --- | --- | --- | --- | --- | --- |
| Sprint-1 | Registration | USN-1 | As a user, I can register by entering my email, password, and confirming my password. | 2 | High | Sri |
| Sprint-1 |  | USN-2 | As a user, I will receive a confirmation email once I have registered. | 1 | High | Sri |
| Sprint-1 | Login | USN-3 | As a user, I can log into the application by entering email & password. | 1 | High | Sri |
| Sprint-1 | Dashboard | USN-4 | As a user, I can view a summary of my complaints with current status. | 2 | High | Sri |
| Sprint-2 | Raise Complaint | USN-5 | As a user, I can raise a complaint with category, description, and attachments. | 3 | High | Sri |
| Sprint-2 | Track Complaint | USN-6 | As a user, I can track the real-time status and timeline of my complaint. | 2 | High | Sri |
| Sprint-2 | Agent Dashboard | USN-9 | As an agent, I can view all complaints assigned to me. | 2 | High | Sri |
| Sprint-2 | Update Status | USN-10 | As an agent, I can update the status of an assigned complaint. | 2 | High | Sri |
| Sprint-3 | Chat | USN-7 | As a user, I can chat in real time with the agent assigned to my complaint. | 3 | Medium | Sri |
| Sprint-3 | Feedback | USN-8 | As a user, I can rate and give feedback once my complaint is resolved. | 1 | Medium | Sri |
| Sprint-3 | Manage Users | USN-12 | As an admin, I can view, activate, or deactivate accounts. | 2 | High | Sri |
| Sprint-3 | Assign Complaints | USN-13 | As an admin, I can assign or reassign complaints to agents. | 2 | High | Sri |
| Sprint-4 | Manage Categories | USN-14 | As an admin, I can create, edit, or remove complaint categories. | 1 | Medium | Sri |
| Sprint-4 | Reports & Analytics | USN-15 | As an admin, I can view dashboard analytics on complaint volume and resolution time. | 3 | Medium | Sri |
| Sprint-4 | UI Polish | USN-16 | As a user, I can switch between light and dark mode for comfortable viewing. | 1 | Low | Sri |

Project Tracker, Velocity & Burndown Chart (4 Marks)

| Sprint | Total Story Points | Duration | Sprint Start Date | Sprint End Date (Planned) | Story Points Completed | Sprint Release Date (Actual) |
| --- | --- | --- | --- | --- | --- | --- |
| Sprint-1 | 6 | 6 Days | 01 Jun 2026 | 06 Jun 2026 | 6 | 06 Jun 2026 |
| Sprint-2 | 9 | 6 Days | 08 Jun 2026 | 13 Jun 2026 | 9 | 13 Jun 2026 |
| Sprint-3 | 8 | 6 Days | 15 Jun 2026 | 20 Jun 2026 | 8 | 21 Jun 2026 |
| Sprint-4 | 5 | 6 Days | 22 Jun 2026 | 27 Jun 2026 | 5 | 27 Jun 2026 |

Velocity:

Assuming a 6-day sprint duration and total story points of 28 completed across 4 sprints, the team's average velocity (AV) per iteration unit is calculated as:

AV (story points/day) = Total Story Points Completed ÷ Total Sprint Duration (days) = 28 ÷ 24 ≈ 1.17 points/day

Burndown Chart:

A burndown chart is a graphical representation of work left to do versus time. It is often used in agile software development methodologies such as Scrum. The chart below tracks the Customer Registry project's remaining story points across the 4 sprints (24-day release):